## Preparatory works Status for HD
Preparatory Works Status for Ground Kavach(NGP-JSG) |  |  |  | Remark | Updated ON
Item | Scope | Progress/Status | Balance |  | 22.10.25
Survey for Gradient Verification and absolute locations information required for Kavach through LiDAR(RKM) | 614 | 265 | 349 | R: TDC: 30.12.2025. BSP: TDC30.11.2025 | 04.11.2025
Survey for space in existing relay rooms for Equipment Installation(Locations) | 285 | 285 | 0
Survey for Availability of Power Supply at Stations/Auto Huts/LC Gates to cater extra load of Kavach(Locations) | 285 | 285 | 0
Survey for Spare Relay Contact Analysis (Stations-23/Raipur, Auto Hut-84/NGP, Auto Hut-6/R, Auto Hut-8/BSP(Locations) | 121 | 78 | 43
Status of Completion SIPs(Stations) | 81 | 78 | 3 | KRL, JMG, KDTR
Status of Completion RCC(Stations) | 81 | 76 | 5 | KRL, JMG, KDTR, UKR, SZB
Status of Completion Cricuit Diagrams(Nos.) | 285 | 277 | 8 | KRL, JMG, KDTR, UKR, SZB, DGS, NPI, G
Details for LC Gate Closure(BSP-38, R-84, NGP-84)(Nos.) | 147 | 8 | 139
Details of PSR(Nos.) | 576 | 576 | All PSR Data is available
Preparatory Works Status for Tower (HDN Route)
Item | Scope | Progress | Balance
RSSI Survey for Tower Locations | 108 | 108 | 0
Physical Site Survey to assess the feasibility of Tower Erection(NGP-46, R- 25, BSP-37) | 108 | 108 | 0
Joint Site Survey and marking for finalzation of Tower Locations at Supervisor Level | 108 | 108 | 0
Approval of Tower Location's GAD from Divisional Authorities | 108 | 108 | 0
Soil Bearing Capacity Test for each Tower Location | 108 | 97 | 11
Foundation of Towers | 108 | 39 | 69
Tower Erection | 108 | 25 | 83
Preparatory Works Status for OFC
Item | Scope | Progress | Balance
Joint Survey for Cable Route Plan(No of Block Sections) | 81 | 56 | 25
Approval of Cable Route Plan from Divisional Authorities(No of Block Sections) | 81 | 56 | 25
HDD(kms) | 1228 | 135 | 1093
Ducting(kms) | 4912 | 270 | 4642
OFC Laying(kms) | 4912 | 66 | 4846
Preparatory Works Status for Tower (LDN Route)
Item | Scope | Progress | Balance
RSSI Survey for Tower Locations | 255 | 164 | 91
Physical Site Survey to assess the feasibility of Tower Erection(NGP-46, R- 25, BSP-37) | 255 | 137 | 118
Joint Site Survey and marking for finalzation of Tower Locations at Supervisor Level | 255 | 71 | 184
Approval of Tower Location's GAD from Divisional Authorities | 255 | 48 | 207
Soil Bearing Capacity Test for each Tower Location | 255 | 55 | 200
Foundation of Towers | 255 | 0 | 255
Tower Erection | 255 | 0 | 255

## Preparatory works Status for LD
Preparatory Works Status for Ground Kavach(NGP-JSG) |  |  |  | Remark | Updated ON
Item | Scope | Progress/Status | Balance |  | 22.10.25
Survey for Gradient Verification and absolute locations information required for Kavach through LiDAR(RKM) | 1816 | 0 | 1816 |  | 04.11.2025
Survey for space in existing relay rooms for Equipment Installation(Locations) |  | 285 | -285
Survey for Availability of Power Supply at Stations/Auto Huts/LC Gates to cater extra load of Kavach(Locations) | 285 | 285 | 0
Survey for Spare Relay Contact Analysis (Stations-23/Raipur, Auto Hut-84/NGP, Auto Hut-6/R, Auto Hut-8/BSP(Locations) | 121 | 78 | 43
Status of Completion SIPs(Stations) | 81 | 78 | 3
Status of Completion RCC(Stations) | 81 | 76 | 5
Status of Completion Cricuit Diagrams(Nos.) | 285 | 277 | 8
Details for LC Gate Closure(BSP-38, R-84, NGP-84)(Nos.) | 147 | 8 | 139
Details of PSR(Nos.) | 576 | 576 | All PSR Data is available
Preparatory Works Status for OFC
Item | Scope | Progress | Balance
Joint Survey for Cable Route Plan(No of Block Sections) | 165 | 11 | 154
Approval of Cable Route Plan from Divisional Authorities(No of Block Sections) | 165 | 11 | 154
HDD(kms) | 3632 | 20 | 3612
Ducting(kms) | 14528 | 40 | 14488
OFC Laying(kms) | 14528 | 5 | 14523
Preparatory Works Status for Tower (LDN Route)
Item | Scope | Progress | Balance
RSSI Survey for Tower Locations | 255 | 164 | 91
Physical Site Survey to assess the feasibility of Tower Erection(NGP-46, R- 25, BSP-37) | 255 | 137 | 118
Joint Site Survey and marking for finalzation of Tower Locations at Supervisor Level | 255 | 71 | 184
Approval of Tower Location's GAD from Divisional Authorities | 255 | 48 | 207
Soil Bearing Capacity Test for each Tower Location | 255 | 55 | 200
Foundation of Towers | 255 | 0 | 255
Tower Erection | 255 | 0 | 255

## KAVACH SECTION TARGETED FOR 25-
Works Status for Ground Kavach(NGP-G, 130 RKM)
Section | RKM | RFID |  |  | Stationary Equipments (Stations) |  |  | Stationary Equipments (HUT/LC Gates) |  |  | FAT (Stations) |  |  | FAT (HUT) |  |  | SAT (Stations) |  |  | SAT (HUT) |  |  | Indoor Design Documents (Stations) |  |  | Indoor Design Documents (HUT/LC Gates)
|  | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance
NGP-KAV | 6 | 150 | 0 | 150 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
KAV-KP | 8 | 150 | 0 | 150 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
KP-KNHN | 5 | 150 | 0 | 150 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
KNHN-SAL | 6 | 150 | 0 | 150 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
SAL-CHCR | 7 | 150 | 0 | 150 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
CHCR-TAR | 6 | 150 | 0 | 150 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
TAR-RRL | 6 | 150 | 0 | 150 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
RRL-KT | 9 | 150 | 0 | 150 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
KT-BRD | 10 | 150 | 0 | 150 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
BRD-K | 8 | 150 | 0 | 150 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
K-TMR | 10 | 150 | 0 | 150 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
TMR-MNU | 10 | 150 | 0 | 150 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
MNU-TRO | 10 | 150 | 0 | 150 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
TRO-KWN | 7 | 150 | 0 | 150 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
KWN-GJ | 12 | 150 | 0 | 150 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
GJ-G | 11 | 150 | 0 | 150 | 1 | 0 | 1 | 2 | 0 | 2 | 1 | 0 | 1 | 2 | 0 | 2 | 1 | 0 | 1 | 2 | 0 | 2 | 1 | 0 | 1 | 2 | 0 | 2
| 131 | 2400 | 0 | 2400 | 16 | 0 | 16 | 10 | 0 | 10 | 16 | 0 | 16 | 10 | 0 | 10 | 16 | 0 | 16 | 10 | 0 | 10 | 16 | 0 | 16 | 10 | 0 | 10
Works Status for TOWER(NGP-G, 130 RKM)
Section | RKM | Tower Foundations (Stations) |  |  | Tower Erections (Stations) |  |  | Tower Foundations (Sections) |  |  | Tower Erections (Sections)
|  | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance
NGP-KAV | 6 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1
KAV-KP | 8 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0
KP-KNHN | 5 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KNHN-SAL | 6 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SAL-CHCR | 7 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHCR-TAR | 6 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TAR-RRL | 6 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RRL-KT | 9 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1
KT-BRD | 10 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1
BRD-K | 8 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
K-TMR | 10 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
TMR-MNU | 10 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0
MNU-TRO | 10 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
TRO-KWN | 7 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KWN-GJ | 12 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0
GJ-G | 11 | 1 | 0 | 1 | 1 | 0 | 1 | 2 | 0 | 2 | 2 | 0 | 2
| 131 | 16 | 12 | 4 | 16 | 12 | 4 | 10 | 5 | 6 | 10 | 4 | 6 | 26 | 16 | 10
Works Status for OFC(NGP-G, 130 RKM)
Section | RKM | OFC Ducting(RKM) |  |  | OFC Laying (RKM) |  |  | Outdoor Design Documents(Nos.)
|  | Scope | Completed | Balance | Scope | Completed | Balance | Scope | Completed | Balance
NGP-KAV | 6 | 12 | 0 | 12 | 24 | 0 | 24 | 1 | 1 | 0
KAV-KP | 8 | 16 | 16 | 0 | 32 | 32 | 0 | 1 | 1 | 0
KP-KNHN | 5 | 10 | 9.8 | 0.2 | 20 | 0 | 20 | 1 | 1 | 0
KNHN-SAL | 6 | 12 | 7.684 | 4.316 | 24 | 0 | 24 | 1 | 1 | 0
SAL-CHCR | 7 | 14 | 11.403 | 2.597 | 28 | 0 | 28 | 1 | 1 | 0
CHCR-TAR | 6 | 12 | 2.216 | 9.784 | 24 | 0 | 24 | 1 | 1 | 0
TAR-RRL | 6 | 12 | 0 | 12 | 24 | 0 | 24 | 1 | 1 | 0
RRL-KT | 9 | 18 | 0 | 18 | 36 | 0 | 36 | 1 | 1 | 0
KT-BRD | 10 | 20 | 0 | 20 | 40 | 0 | 40 | 1 | 1 | 0
BRD-K | 8 | 16 | 10.035 | 5.965 | 32 | 0 | 32 | 1 | 1 | 0
K-TMR | 10 | 20 | 0 | 20 | 40 | 0 | 40 | 1 | 1 | 0
TMR-MNU | 10 | 20 | 8.767 | 11.233 | 40 | 0 | 40 | 1 | 1 | 0
MNU-TRO | 10 | 20 | 0 | 20 | 40 | 0 | 40 | 1 | 1 | 0
TRO-KWN | 7 | 14 | 8.124 | 5.876 | 28 | 0 | 28 | 1 | 1 | 0
KWN-GJ | 12 | 24 | 6.641 | 17.359 | 48 | 0 | 48 | 1 | 1 | 0
GJ-G | 11 | 22 | 2.538 | 19.462 | 44 | 0 | 44 | 1 | 1 | 0
| 131 | 262 | 83.208 | 178.792 | 524 | 32 | 492 | 16 | 16 | 0

## Tender status
KAVACH TENDER STATUS on HDN ROUTE | [5 empty] | UPDATED ON: 23.06.2025
01.07.2025
Item | Section | NIT Date | Tender Opening Date (Original/Revised) | LOA Date | Remarks | 07.07.2025
Ground Kavach/Building/Power Supply | NAGPUR-JHARSUGUDA | 04.01.2025 | 10.02.2025/20.02.2025/04.03.2025 |  | LOA issued on 12.06.2025 | 14.07.2025
OFC | NAGPUR-RAIPUR | 12.11.2024 | 13.12.2024 | 21.03.2025 | LOA issued on 21.03.2025 | 21.07.2025
OFC | RAIPUR-CHAMPA | 28.12.2024 | 24.01.2025 | 13.05.2025 | LOA issued on 13.05.2025 | 19.08.25
Tower | NAGPUR-JHARSUGUDA | 21-10-2024 | 29-11-2024 | 15.1.2025 | LOA issued on 15.01.2025 | 25.08.2025
PSSA | NAGPUR-JHARSUGUDA | 24.03.2025 | 09.05.2025 |  | LOA issued on 29.08.2025 | 22.10.2025
27.10.2025
04.11.2025
Tender Status of Ground Kavach(LDN Route, 1563 RKM)
Item | Section | NIT Date | Tender Opening Date (Original/Revised) | LOA Date | Remarks
Ground Kavach/Building/Power Supply | LDN Route | 30.01.2025 | 12.03.2025/26.03.2025 | - | LOA issued on 14.06.2025
OFC | LDN Route | - | - | - | Out of 2 Works, One work is sanctioned by RB. OFC Tender for BSP-KTE Section floated on 14.07.2025. Other work is again returned by RB on 26.08.25. Compliance sent on 17.10.2025.
Tower | LDN Route | 19.12.2024 | 20.01.2025 | - | Tender is discharged due to non-fullfillment of Technical eligibility Criteria
Tower | LDN Route | 26.03.2025 | 02.05.2025 | - | LOA issued on 11.07.2025

## Loco KAVACH
Loco Kavach Status
Loco shed | Loco Holding (Nos) | KAVACH allotment by Railway Board |  |  | Locos fitted with Kavach(Nos) |  |  | Balance(Nos) |  |  | Remarks | Updated on
|  | M/s Kernex | M/s. Medha | Total | M/s Kernex | M/s. Medha | Total | M/s Kernex | M/s. Medha | Total
ELS/BIA | 329 | 90 | 173 | 263 | 0 | 56 | 56 | 90 | 117 | 207 | Material received 56 locos. Fitment done. | 04.11.2025
ELS/BSP | 277 | 173 | 0 | 173 | 0 | 0 | 0 | 173 | 0 | 173
DLS/R | 164 | 115 | 0 | 115 | 0 | 0 | 0 | 115 | 0 | 115
TOTAL | 770 | 378 | 173 | 551 | 0 | 56 | 56 | 378 | 117 | 495

## Training
Status of KAVACH Training | [8 empty] | UPDATED ON: 03.11.2025
S&T Staff | Total Strength | Training provided at |  |  |  |  | Balance | Remarks | 15.09.2025
|  | IRISET | STTC | Other Institute | Total | %Completed |  |  | 26.09.2025
Drawing Officer | 11 | 9 | 0 | 0 | 9 | 81.82% | 2 | 20 officers nominated. | 06.10.2025
Other Officers | 58 | 35 | 0 | 8 | 43 | 74.14% | 15 |  | 13.10.2025
Drawing Supervisor | 15 | 15 | 0 | 0 | 15 | 100% | 0 |  | 22.10.2025
Other Supervisors | 362 | 26 | 35 | 83 | 144 | 39.78% | 218 | 31 nominated. | 27.10.2025
Staff | 1031 | 0 | 343 | 63 | 406 | 39.38% | 625 | 97 nominated | 28.10.2025
Total | 1477 | 85 | 378 | 154 | 617 | 41.77% | 860 |  | 03.11.2025
Operating Staff | Strength | Training provided at |  |  |  | %Completed | Balance | Remarks | Updated on
|  | IRISET | MDZTI | other institute | Total
Officers | 49 | 3 | 0 | 0 | 3 | 6.122% | 46 |  | 07.11.2025
DTI/CSM/SM/ASM/CHC | 1436 | 0 | 381 | 130 | 511 | 35.58% | 925
Train Manager | 2924 | 0 | 1067 | 0 | 1067 | 36.49% | 1857
Other Staff | 2251 | 0 | 307 | 0 | 307 | 13.64% | 1944
Total | 6660 | 3 | 1755 | 130 | 1888 | 28.35% | 4772
Electrical | Strength | Training provided at |  |  |  |  | Balance | Remarks | Updated on
|  | IRISET | ELTC | other institute | Total | %Completed
Officers | 18 | 18 | 0 | 0 | 18 | 100% | 0 |  | 03.11.2025(One batch will be complete on 05.11.2025)
LI | 263 | 241 | 0 | 0 | 241 | 91.63% | 22
LP/ALP | 7489 | 0 | 2325 | 0 | 2325 | 31.05% | 5164
Other Staff (Shed) | 122 | 22 | 0 | 118 | 140 | 114.8% | -18 | 18 supervisors are trained both (IRISET & other institute also).
Total | 7892 | 281 | 2325 | 118 | 2724 | 34.52% | 5168
LIST OF ELECTRICAL OFFICER TO BE NOMINATED / COMPLETED FOR TRAINING ON KAVACH AT IRISET as on 07.08.25
[7 empty] | Sl.No | DATE | NAME OF THE OFFICER | DIGNATION | Remarks
[7 empty] | 1 | 17/12/24 to 18/12/24 | Sri.Peeyoosh Gupta | CELE/SECR | Training Completed
[7 empty] | 2 | 17/12/24 to 18/12/24 | Sri.O.P Soni | ADEE/OP/BSP
[7 empty] | 3 | 03/02/25 TO 07/08/25 | Sri.Shashank Koshta | Sr.DEE/TRS/BSP
[7 empty] | 4 | 04/09/23 TO 06/09/23 | Sri.Pranesh Kumar | DEE/TRS/BIA
[7 empty] | 5 | 30/07/25 to 01/08/25 | Sri.Pankaj Kumar Singh | DEE/DLS/RAIPUR
[7 empty] | 6 | 05/08/25 to 07/08/25 | Sri.Bharat Babu Kotarya | ADEE/TRS/BIA
[7 empty] | 7 | 20/08/25 to 22/08/25 | Sri .Amit Gupta | Sr.DEE/TRS/BIA | Training Completed
[9 empty] | Md.Masud Alam | Sr.DEE/OP/BSP
[9 empty] | Sri.Duregesh Maneshwar | DEE/TRS/BSP
[9 empty] | Sri. A.Prasad Rao | ADEE/DLS/R
[7 empty] | 8 | 15/09/25 to 17/09/25 | Sri.Saurabh Davaggar | Sr.DME/D/R | Nominated
[9 empty] | Sri.C.B.K Singh | ADEE/OP/SDL
[9 empty] | Sri.Prashant Shukala | ADEE/TRS/BSP
[9 empty] | SriPradip kumar Saha | ADEE/OP/NGP
[7 empty] | 9 | 08/10/25 to 10/10/25 | Md.Waseem siddiqui | Sr.DEE/OP/NGP
[9 empty] | Sri.Anurag Tiwary | Sr.DEE/OP/NGP
[9 empty] | Sri.Shyam Kurrey | ADE/OP/R
[9 empty] | Sri.M.S Thakur | ADME/D/R

## EI Works
# | Stations | PH | New/Replacement | Tender | ESP | SIP | CRS Sanction | Building/TDC | Indoor Progress (%) | Outdoor Progress (%) | TDC | Executive Agency | Remarks
1 | Raigarh | 15 | Replacement | Awarded | Approved | Approved | Obtained 14.08.25 | Completed | 100% | 100% | Commissioned | CSTE/Con
2 | Kirodimal Nagar | 15 | Replacement | Awarded | Approved | Approved | Obtained 07.08.25 | Completed | 100% | 100% | Commissioned | CSTE/Con
3 | Madwarani | 15 | Replacement | Awarded | Approved | Approved | 31.10.2025 | Electrical Wiring is pendingat East Goomty and AT Supply is pending at Centrem East and West/15.11.25 | 30% | 50% | Jan’26 | CSTE/Project-II | CRS Application pending for Grade condonation & LC Gate GAD.
4 | Korba | 33 | Replacement | Awarded | Approved | Approved | Pending | Completed | 80% | 80% | Feb’26 | CSTE/Con
5 | Kurud | 14 | New | Awarded | Approved | Approved | Obtained 04.03.25 | Completed | 98% | 98% | Oct’25 | CSTE/Con
6 | Baraduar | 15 | Replacement | Awarded | Approved | Approved | Obtained 14.06.24 | Completed | 95% | 90% | Oct’25 | CSTE/Con
7 | Saragaon | 15 | Replacement | Awarded | Approved | Approved | Submited | Completed | 90% | 90% | Oct’25 | CSTE/Con
8 | Gevra Raod | Deposit | Replacement | Awarded | Approved | Approved | Pending | Pending TDC:30.11.2025 | 10% | 25% | Feb’26 | CSTE/Project-II | Sectioning Diagram Appendix- G and Grade Condonation, LC GAD are pending. TDC: 30.10.25
9 | Pendra Road | Deposit | Replacement | Awarded | Approved | Approved | Application sent on 05.10.2025 but CRS returned the file citing non-availability of Grade Condonation Paper. | Not Completed. Neither Centre nor Goomties are completed TDC: Nov'25 | 0% | 55% | Nov’25/Jan'26 | CSTE/Project-II | CRS application not accepted due to not availability of Grade condo nation.
10 | Tumsar Road | 15 | Alteration | Awarded | Approved | Approved | Submited 26.08.25 | Completed | 80% | 70% | Nov’25 | CSTE/Con
11 | Akaltara | 15 | Replacement | Awarded | Approved | Approved | U/Preparation | Completed | 60% | 70% | Dec’25 | CSTE/Con
12 | Champa | 15 | Replacement | Awarded | Approved | Approved | U/Preparation | Completed | 10% | 20% | Feb’26 | CSTE/Con
13 | Naila | 15 | Alteration | Awarded | Approved | Approved | U/Preparation | Completed | 20% | 70% | Dec’25 | CSTE/Con
14 | Dadhapara | 15 | Replacement | Awarded | Approved | Approved | Pending | Not Completed/Oct’25 | 0% | 15% | Mar’26 | CSTE/Con
15 | Dagori | 15 | Replacement | Awarded | Approved | Approved | Pending | Not Completed/Oct’25 | 0% | 15% | Mar’26 | CSTE/Con
16 | Belha | 15 | Replacement | Awarded | Approved | Approved | Pending | Not Completed/Oct’25 | 0% | 15% | Mar’26 | CSTE/Con
18 | Surajpur Road | 15 | Replacement | Awarded | Approved | Approved | U/Preparation | 25.09.2025 | 5% | 25% | Feb’26 | CSTE/Con
17 | Sheoprasad Nagar | 15 | Alteration | Awarded | Approved | Approved | U/Preparation | Not required | 0% | 20% | Feb’26 | CSTE/Con
19 | Katora | 15 | Replacement | Awarded | Approved | Approved | U/Preparation | 30.09.2025 | 5% | 15% | Feb’26 | CSTE/Con
20 | Baikunthpur | 15 | Replacement | Awarded | Approved | Approved | U/Preparation | 15.10.2025 | 0% | 15% | Feb’26 | CSTE/Con
21 | Dhamtari | 15 | New | Awarded | Approved | Approved | Obtained 29.08.25 | Completed | 0% | 10% | Dec’25 | CSTE/Con
22 | Kharsia | 15 | Alteration | floated | Approved | Approved | Pending | Not required | 0% | 0% | May’26 | CSTE/Con
23 | Bakal | 15 | Replacement | Awarded | Approved | Approved | Pending | Not Completed /Oct’25 | 0% | 10% | Feb’26 | CSTE/Con
24 | Rajnandgaon | 15 | Replacement | Awarded | Approved | Approved | Pending | Not Completed/Oct’25 | 0% | 10% | Feb’26 | CSTE/Con
25 | Jharadih | 15 | Alteration | flooated | Approved | Approved | Pending | Not required | 0% | 0% | May’26 | CSTE/Con
26 | Itwari | 15 | Replacement | Awarded | Approved | Approved | Pending | Center goomty handed over by MRIDC & Both end goomty yet to be handed over. | 0% | 0% | Dec’25 | CSTE/Con
27 | Musra | 15 | Replacement | Awarded | Approved | Approved | Pending | Not Completed/Oct’25 | 0% | 10% | Feb’26 | CSTE/Con
28 | Kargi road | 15 | Replacement | Awarded | Approved (06.10.2025) | Approved (Alteration: Under approval) | Pending TDC:15.11.25 | Not Completed Nov'25 | 0% | 35% | Jan'26 | CSTE/Project-II | Kargi Revised ESP is approved on 06.10.2025. SIP is under approval. TDC:05.11.2025
29 | Balpur | 33 | Replacement | Awarded | Approved | Approved | Pending (PCSTE Approval) | Not Completed/Nov'25 | 0% | 10% | Jan'26 | CSTE/Project-II | Building Work is under progress. TDC: 30.11.25
30 | Nagpur Road | 15 | New | Under TC | Approved | Pending | Pending | Not started | 0% | 0% | Mar’27 | CSTE/Con
31 | Nagar | 15 | Replacement | Under TC | Approved | Pending | Pending | Not started | 0% | 0% | Mar’27 | CSTE/Con
32 | Darritola | 15 | Replacement | Under TC | Approved | Pending | Pending | Not started | 0% | 0% | Mar’27 | CSTE/Con
33 | Udalkachar | 15 | Replacement | Under TC | Approved | Approved | Pending | Not started | 0% | 0% | Mar’27 | CSTE/Con
34 | Boridand | 15 | Replacement | Under TC | Approved | Pending | Pending | Not started | 0% | 0% | Mar’27 | CSTE/Con
35 | Nipania | 15 | Replacement | Awarded | Approved | Approved | Pending | Not started | 0% | 0% | Feb'26 | CSTE/Con
36 | Bhatapara | 15 | Replacement | Awarded | Approved | Approved | Pending | Not started | 0% | 0% | Mar’26 | CSTE/Con
37 | Hathband | 15 | Replacement | Awarded | Approved | Approved | Pending | Not started | 0% | 0% | Mar’26 | CSTE/Con
38 | Bhilai | 15 | Replacement | Awarded | Approved | Approved | Pending | Not started | 0% | 0% | Dec'26 | CSTE/Con
39 | Bhilai Nagar | 15 | Replacement | Awarded | Approved | Approved | Pending | Not started | 0% | 0% | Dec'26 | CSTE/Con
40 | Durg Block Junction Cabin | 15 | Replacement | floated | Not approved | Not approved | Pending | Not started | 0% | 0% | Jun'27 | CSTE/Con
41 | Durg | 33 | Replacement | floated | Not approved | Not approved | Pending | Not started | 0% | 0% | Jun'27 | CSTE/Con
42 | Kumhari | 33 | Replacement | To be floated | Not approved | Not approved | Pending | Not started | 0% | 0% | Jun'27 | CSTE/Con
43 | Sarona | 33 | Replacement | To be floated | Not approved | Not approved | Pending | Not started | 0% | 0% | Jun'27 | CSTE/Con
44 | Bilaspur | 33 | Replacement | Awarded | Approved | Approved | Pending | Completed | 30% | 35% | Aug'26 | CSTE/Project-II
45 | Kothari Road | 33 | Replacement | Awarded | Approved | Approved | obtained | Completed | 100% | 100% | Commissioned | DRM/BSP
46 | Urga | 33 | Replacement | Awarded | Approved | Approved | obtained | Completed | Completed | Completed | Commissioned | CSTE/Project-II
47 | ORE Yard | Deposit | Replacement | Awarded | Approved | Under Approval | Not required | Not started | 0% | 0% |  | DRM/R
48 | Bhanwartonk | 33 | Replacement | Opened TDC:5.11.25 | Approved | Under Preparation TDC:30.11.25 | Pending TDC:15.01.26 | Not started | 0% | 0% | Aug'26 | CSTE/Project-II
49 | A-Cabin | 33 | Replacement | Awarded | Approved | Working SIP Approved | Pending (PCSTE Approval) | TDC Dec'2025 | 0% | 30% | Jan’26 | CSTE/Project-I
50 | Coal Load East & West Yard BMY | 33 | Replacement | Awarded | Approved | Under Approval | Pending (PCSTE Approval) | TDC Jan 2026 | 0% | 3% | Feb’26 | CSTE/Project-I
51 | Coal Empty East & West Yard BMY | 33 | Replacement | Awarded | Approved | Under Approval | Pending (PCSTE Approval) | TDC Jan 2026 | 0% | 2% | Mar’26 | CSTE/Project-I
52 | Chakradhar Nagar | Deposit | New | Awarded | Approved | Approved | Application resubmitted on 13.10.2025. Observation compliance sent on 23.10.2025 | Completed | 98% | 95% | Oct'25 | CSTE/Project-I
53 | Bhaitola | Deposit | Replacement | not awarded | Approved | Not approved | Pending | not started | 0% | 0% | Mar’27 | RITES
54 | Ramtek | 33 | Replacement | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
55 | Dhumrikhurud | 33 | Replacement | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
56 | Goberwahi | 33 | Replacement | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
57 | Dongri Buzurg | 33 | Replacement | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
58 | Waraseoni | 33 | Replacement | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
59 | Birsola | 33 | Replacement | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
60 | Hatta | 33 | Replacement | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
61 | Baikunth | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
62 | Tilda | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
63 | C-Cabin BMY | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
64 | D-Cabin BMY | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
65 | E-Cabin BMY | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
66 | P-Cabin BMY | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
67 | FMY Yard-BMY | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
68 | Exchange Yard BMY | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-I
69 | Bishrampur | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
70 | Kamalpur gram | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
71 | Ambikapur | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
72 | Karonji | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
73 | Mauhari | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
74 | Harrad | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
75 | Kotma | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
76 | Bijuri | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
77 | Manendragarh | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
78 | Paradol | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
79 | Chirimiri | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
80 | Ghutku | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
81 | Kalmitar | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
82 | PLAU | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II
83 | Kusmunda | 33 | New | To be floated | Not approved | Not approved | Pending | not started | 0% | 0% |  | CSTE/Project-II

## Auto-Signalling
| Div | Section | Target (RKM) | Completed (RKM) | Balance (RKM) | ESP Status | SIP Status | RCC | SWR & SWRD | Interface Drawing | Application Logic' | FAT | SAT | Tender Status | Indoor Progress (%) | Outdoor Progress (%) | GM Sanction | TDC
1 | BSP | Raigarh-Kotarlia | 9 | 0 | 9 | Approved | Approved | Approved | Approved | Approved | Approved | Completed | Completed | Awarded | 100% | 100% | Not obtained 12.10.25 03.11.25 | Oct’25 Nov'25
2 | BSP | Kotarlia-Jamga** | 9 | 9 | 0 | Approved | Approved | Approved | Approved | Approved | Approved | Completed | Completed | Awarded | 100% | 100% | Obtained | Commissioned
3 | BSP | Jamga-Daghora | 12 | 0 | 12 | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Pending | Awarded | 10% | 20% | Not obtained 5.01.26 | Jan’26
4 | BSP | Daghora-Himgiri | 7 | 0 | 7 | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Pending | Awarded | 0% | 0% | Not obtained 15.02.26 | Feb’26
5 | BSP | Champa-Saragaon | 10 | 10 | 0 | Approved | Approved | Approved | Approved | Approved | Approved | Completed | Completed | Awarded | 100% | 100% | Obtained | Commissioned
6 | BSP | Saragaon-Baraduar | 5 | 0 | 5 | Approved | Approved | Approved | Approved | Approved | Pending | Pending | Pending | Awarded | 60% | 90% | Not obtained 30.11.25 | Oct’25 Dec'25
7 | BSP | Baraduar-Sakti | 15 | 0 | 15 | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Pending | Awarded | 30% | 60% | Not obtained 30.11.25 | Mar’26
8 | BSP | Sakti-SPGCL | 29 | 0 | 29 | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Pending | Awarded | 0% | 15% | Not obtained 5.01.26 | Mar’26
9 | BSP | Pendra Road- Venkatnagar | 19 | 0 | 19 | Approved | Under Approval | Under Approval | Pending | Pending | Pending | Pending | Pending | Awarded | 0% | 40% | Not obtained 20.12.25 | Feb’26
10 | R | Raipur-Mandhar | 12 | 0 | 12 | Approved | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Awarded | 10% | 70% | Not obtained 01.11.25 | Nov’25
11 | R | Urkura-Sarona | 11 | 11 | 0 | Approved | Approved | Approved | Approved | Approved | Approved | Completed | Completed | Awarded | 100% | 100% | Obtained | Commissioned
12 | R | Mandhar-Silyari-Baikunth | 11 | 0 | 11 | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Pending | Awarded | 0% | 0% | Not obtained 30.11.25 | Jan’26
13 | R | Baikunth-Tilda | 10 | 0 | 10 | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Pending | Awarded | 0% | 10% | Not obtained 30.12.25 | Feb’26
14 | R | Tilda-Hathband | 15 | 0 | 15 | Approved | Approved | Pending | Pending | Pending | Pending | NA | NA | Awarded | 0% | 5% | Not obtained 30.1.26 | Mar’26
15 | R | Dagori-Nipania** | 9 | 9 | 0 | Approved | Approved | Approved | Approved | Approved | Approved | Completed | Completed | Awarded | 100% | 100% | Obtained | Commissioned
16 | R | Nipania-Bhatapara | 15 | 0 | 15 | Approved | Approved | Approved | Approved | Approved | Approved | NA | NA | Awarded | 90% | 85% | Submitted | Oct'25 Nov'25
17 | R | Bhatapara-Hathbandh | 15 | 0 | 15 | Approved | Approved | Approved | Pending | Pending | Pending | NA | NA | Awarded | 10% | 40% | Not obtained 14.11.25 | Dec’25
18 | R | Raipur-Lakholi | 29 | 0 | 29 | Approved | Under Prepataion | Pending | Pending | Pending | Pending | Pending | Pending | Not Awarded | 0% | 0% | Not obtained | Jun'26
19 | NGP | Ghangajhari-Gudma** | 26 | 26 | 0 | Approved | Approved | Approved | Approved | Approved | Approved | Completed | Completed | Awarded | 100% | 100% | CRS Sanction obtained. | Commissioned
20 | NGP | Kalumana Jn-Godhani | 8 | 0 | 8 | Approved | Approved | Pending | Pending | Pending | Pending | Pending | Pending | Awarded | 5% | 10% | Not obtained 30.1.26 | Mar’26
21 | BSP | Jharsugda-IB-BRJN | 10 | 0 | 10 | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Pending | Awarded | 10% | 50% | Not obtained 10.11.25 | Mar’26
|  | Total Target | 276 | 65 | 211
** Spillover Target 2024-25
|  | Section | Target (RKM) | TDC
|  | Kotarlia-Jamga** | 9 | Commissioned
|  | Dagori-Nipania** | 9 | Commissioned
|  | Ghangajhari-Gudma** | 26 | Commissioned
|  | Champa-Saragaon | 10 | Commissioned
|  | Total (A) | 54
|  | Total Target (B) | 277
|  | Net Target 25-26 (B-A) | 223
22 | BSP | Raigargh-Kirodimalnagar | 8 | 0 | 8 | Approved | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Awarded | 10% | 80% | Not obtained 30.11.25 | Dec'25
22 | BSP | Kirodimalnagar-Robertson | 17 | 0 | 17 | Approved | Approved | Approved | Approved | Pending | Pending | Pending | Pending | Awarded | 5% | 60% | Not obtained 30.01.26 | Feb'26

## EI Drawing
Srl No. | Name of the work | TDC | Station involved | SIP | RCC | SWRD | SWR | - Appen- G | Grade Condonation | CRS/GM Application | Remarks | Dy cste
1 | Pendra Road Yard remodeling withEI (TDC:30.12.25) (M/s Arihant Con) | 30.12.25 | Pendra Road (PND) (ESP-Approved) | Y | Y | Y | Y | Y | 10.10.25 | Y | CRS application not accepted due to not availability of Grade condo nation. | Dy.CSTE(project)-II
2 | Gevra Road Yard remodeling with EI (TDC:30.26) (M/s MRT) | 30.01.26 | Gevra Road ( GAD) (ESP-Approved) | Y | 10.10.25 | 15.10.25 | 20.10.25 | 25.10.25 | 20.10.25 | 30.10.25 | Sectioning Diagram Appendix- G are pending with Division. TDC: 25.10.25 | Dy.CSTE(project)-II
3 | MDWARANI Additional Loop with EI (TDC:30.12.25) (M/s Tirupati) | 30.12.25 | MDWARANI (MWRN) (ESP-Approved) | Y | Y | 15.10.25 | 15.10.25 | Y | 20.10.25 | 20.10.25 | SWR & SWRD are under signature of Division. TDC:10.10.25 | Dy.CSTE(project)-II
4 | BALPUR Replacement PI to EI (TDC:25.01.25) (M/s DKC) | 25.01.25 | BALPUR (BPRH) (ESP-Approved) | Y | Y | 10.11.25 | 10.11.25 | _ | - | 15.11.25 | Building Work is under progress. TDC: 30.11.25 | Dy.CSTE(project)-II
5 | Kargi Road-Salka Road 3rd Line (TDC:30.01.25) (M/s MRT) | 30.01.25 | KARGI ROAD ( KGB) (ESP-Under Revision) | 25.10.25 | 15.11.25 | 25.11.25 | 25.11.25 | 25.10.25 | 10.11.25 | 30.11.25 | Kargi Revised ESP is pending for approval. TDC: 20.10.2025 | Dy.CSTE(project)-II
| Kargi Road-Salka Road 3rd Line (TDC:30.01.25) (M/s MRT) | 30.01.25 | SALKA ROAD (SLKR) (ESP-Approved) | Y | 20.10.25 | 15.11.25 | 15.11.25 | 25.10.25 | 10.11.25 | 20.11.25 | ESP has been revised with the provision of additional X-over. | Dy.CSTE(project)-II
6 | Khongsara--Bhanwartonk--Khodri Dn Line to Bi-directional Line. (TDC:30.02.26) (M/s Aanand Enterprise) | 30.02.26 | Khongsara (ESP-Approved) | Y | Y | 20.10.25 | 20.10.25 | Y | Y | 20.10.25 | ESP has been revised.SWR & SWRD under revision. | Dy.CSTE(project)-II
| Khongsara--Bhanwartonk--Khodri Dn Line to Bi-directional Line. (TDC:30.02.26) (M/s Aanand Enterprise) | 30.02.26 | Bhanwartonk (BHTK)(ESP-Approved) | Y | Y | 20.10.25 | 20.10.25 | Y | Y | 30.10.25 |  | Dy.CSTE(project)-II
| Khongsara--Bhanwartonk--Khodri Dn Line to Bi-directional Line. (TDC:30.02.26) (M/s Aanand Enterprise) | 30.02.26 | Khodri ( KOI) (ESP-Approved) | Y | Y | 20.10.25 | 20.10.25 | Y | Y | 30.10.25 |  | Dy.CSTE(project)-II
7 | Pendra Road-Harri-Venkat Nagar Auto Signalling. (M/s KRIL Tirupati JV TDC: 30.02.25) | 30.02.25 | Pendra Road (PND) | 05.11.25 | 10.11.25 | 25.11.25 | 25.11.25 | _ | _ | 20.12.25 | Outdoor Work is under Progress. TDC:30.12.2025 | Dy.CSTE(project)-II
| Pendra Road-Harri-Venkat Nagar Auto Signalling. (M/s KRIL Tirupati JV TDC: 30.02.25) | 30.02.25 | Harri(HRB) | 05.11.25 | 10.11.25 | 25.11.25 | 25.11.25 | _ | _ | 20.12.25 | Outdoor Work is under Progress. TDC:30.12.2025 | Dy.CSTE(project)-II
| Pendra Road-Harri-Venkat Nagar Auto Signalling. (M/s KRIL Tirupati JV TDC: 30.02.25) | 30.02.25 | Venkat Nagar(VKR) | 05.11.25 | 10.11.25 | 25.11.25 | 25.11.25 | 10.12.25 | _ | 20.12.25 | Outdoor Work is under Progress. TDC:30.01.2025 | Dy.CSTE(project)-II
8 | Raigargh-Chakradharnagar-Kotarlia Auto Sec. (TDC:15.10.2025) (M/s Texmeco & Ms Kyosan) | 15.10.2025 | Raigargh (RIG)- Chakradharnagar (CKR)- Kotalia(KRL) | Y | Y | Y | Y | _ | _ | 12.10.25 | Training Done. SAG Inspection done on 15.10.25 | Dy.CSTE(project)-RIG @ BSP
9 | Jharsugda-Brajrajnagar Auto Signal. (TDC: 15.11.26) (M/s MRT) | 15.11.26 | Jharsugda (JSG) IB Brajrajnagar (BRJN) | Y | Y | 10.10.25 | 15.10.25 | _ | _ | 10 .11.25 | SAG inspection: 30.10.25 ( Signal: 12/33) Training certificate: 25.10.25 | Dy.CSTE(project)-RIG @ BSP
10 | Raigargh-JSPL-Kirodimalnagar. (TDC: 20.11.25) (M/s V Wargsis) | 20.11.25 | Raigargh (RIG) JSPL Kirodimalnagar (KDTR) | Y | 15.10.25 | 15.10.25 | 20.10.25 | _ | _ | 30.10.25 | SAG inspection: 25.10.2025 ( Signal: 03/09) Training certificate: 10.10.25 | Dy.CSTE(project)-RIG @ BSP
11 | Saragaon-Baraduar-Sakti Auto Section. (TDC:15.12.2025) (M/s RVNL) | 15.12.2025 | Saragaon (SRGD), Baraduar(BUA), Sakti. (SKT) | Y | 10.10.25 | 12.10.25 | 20.10.25 | _ | _ | 30.11.25 | SAG inspection: 15.11.2025 ( Signal: 16/48) Training certificate: 20.10.25 | Dy.CSTE(project)-RIG @ BSP
12 | Kirodimalnagar-Bhupdeopur-SPGCL- Robertson. ( TDC: 15.01.26) (M/s V Wargsis) | 15.01.26 | Kirodimalnagar (KDTR) Bhupdeopur (BEF) SPGCL Robertson (ROB). | Y | 30.10.25 | 15.10.25 | 20.10.25 | _ | _ | 10.12.25 | SAG inspection: 05.12.25 ( Signal: 04/42) Training certificate: 30.10.25 | Dy.CSTE(project)-RIG @ BSP
13 | Sakti-Jharadih-Kharsia. ( TDC:15.01.26) (M/s MRT) | 15.01.26 | Sakti(SKT) Jaradihi(JDI) Kharsia(KHS). | Y | 30.10.25 | 15.11.25 | 20.11.25 | _ | _ | 05.01.26 | SAG inspection: 05.12.25 ( Signal: 04/32) Training certificate: 30.11.25 | Dy.CSTE(project)-RIG @ BSP
14 | Brajrajnagar-Lajkura- Belpahar. ( TDC:15.02.26) (M/s MRT) | 15.02.26 | Brajrajnagar (BRJN) Lajkura(LJKR) Belpahar((BPH)) | Y | 30.10.25 | 15.11.25 | 25.11.25 | _ | _ | 10.02.26 | SAG inspection: 05.02.26 ( Signal: 00/20) Training certificate: 25.10.25 | Dy.CSTE(project)-RIG @ BSP
15 | Jamga-Dagora Auto ( TDC:15.01.26) (M/s Texmaco) | 15.01.26 | Jamga( JMG) Dagora(DAO) | Y | 15.11.25 | 15.10.25 | 15.10.25 | _ | _ | 05.01.25 | SAG inspection: 15.12.25 ( Signal: 00/48) Training certificate: 25.11.25 | Dy.CSTE(project)-RIG @ BSP
16 | Kharsia-Robertsion Auto. ( TDC:15.04.26) (M/s MRT) | 15.04.26 | Kharsia (KHS). Robertsion (ROB) | Y | 25.11.25 | 15.11.25 | 20.11.25 | _ | _ | 05.01.26 | SAG inspection: 05.02.26 ( Signal: 04/32) Training certificate: 30.01.26 | Dy.CSTE(project)-RIG @ BSP
17 | Belpahar-Himgir Auto Section. ( TDC:15.05.26) (M/s MRT) | 15.05.26 | Belpahar(BPH) Himgir(HGR) | Y | 30.01.26 | 15.01.26 | 25.01.26 | _ | _ | 20.04.26 | SAG inspection: 15.04.26 ( Signal: 00/54) Training certificate: 15.02.26 | Dy.CSTE(project)-RIG @ BSP
18 | Dagora-ACBPL-Himgir. ( TDC:15.03.26) (M/s Texmaco) | 15.03.26 | Dagora(DAO) ACBPL Himgir(HGR) | Y | 15.12.25 | 20.12.25 | 24.12.25 | _ | _ | 15.02.26 | SAG inspection: 10.01.26 ( Signal: 00/12) Training certificate: 15.12.25 | Dy.CSTE(project)-RIG @ BSP
19 | Chakradharnagar Station with EI (TDC:15.10.2025) (M/s Texmeco & Ms Kyosan) | 15.10.2025 | Chakradhar Nagar(ESP- Approved) | Y | Y | Y | Y | Y | Y | Y | CRS application resubmitted on 07.10.25 | Dy.CSTE(project)-RIG @ BSP
20 | Raipur-Urkura-Mandhar Auto Sec. (TDC: 30.11.25 ) (M/s Texmeco ) | 30.11.25 | Raipur (R) Urkura (URK) Mandhar P-I(MDH) | Y | Y | 10.10.25 | 15.10.25 | _ | _ | 25.11.25 | SAG inspection: 20.11.25 ( Signal: 02/14) Training certificate: 22.10.25 | Dy.CSTE(project)-R
21 | Mandhar-Silyari-Baikunth Auto Sec (TDC: 15.01.26) (M/s Texmaco) | 15.01.26 | Mandhar P-II(MDH) Siliyari (SLH) Baikunth P-I(BKTH) | Y | 15.11.25 | 15.11.25 | 25.11.25 | _ | _ | 30.11.25 | SAG inspection: 24.11.25 ( Signal: 00/38) Training certificate: 28.11.25 | Dy.CSTE(project)-R
22 | Baikunth-Tilda Auto Sec (TDC: 15.02.26) (M/s Texmaco) | 15.02.26 | Baikunth P-II(BKTH) Tilda P-I (TLD) | Y | 30.10.25 | 25.10.25 | 15.11.25 | _ | _ | 30.01.26 | SAG inspection: 22.01.26 ( Signal: 00/08) Training certificate: 27.12.25 | Dy.CSTE(project)-R
23 | Tilda- Hathbandh Auto Sec (TDC: 15.02.26) (M/s Texmaco) | 15.02.26 | Tilda P-II(TLD) Hathband P-II(HN) | Y | 25.11.25 | 20.11.25 | 15.12.25 | _ | _ | 15.01.26 | SAG inspection: 05.01.26 ( Signal: 00/24) Training certificate: 10.01.26 | Dy.CSTE(project)-R
24 | Nipania- Bhatapara Auto Sec (TDC: 15.10.25) (M/s Texmaco) | 15.10.25 | Nipania (NPI) Bhatapara P-I(BYT) | Y | Y | Y | Y | _ | _ | 04.10.25 | SAG inspection: 26.09.25 (Signal :40/40) Training certificate: 08.10.25 | Dy.CSTE(project)-R
25 | Bhatapara-Hathbandh Auto Sec (TDC: 15.12.25) (M/s Texmaco) | 15.12.25 | Bhatapara P-II(BYT) Hathbandh P-I(HN) | Y | 20.10.25 | 25.10.25 | 10.11.25 | _ | _ | 14.11.25 | SAG inspection: 08.11.25 ( Signal: 00/36) Training certificate: 11.11.25 | Dy.CSTE(project)-R
26 | A-Cabin Replacement PI to EI (TDC:15.01.26) (M/s KRIL Tirupati JV) | 15.01.26 | A Cabin(ESP-Under Approval) | Y | 31.10.25 | 27.10.25 | 15.11.25 | 02.11.25 | _ | 15.12.25 | Building Work is under progress. TDC-10.12.25 | Dy.CSTE(project)-R
27 | Coal Load Yard Replacement PI to EI (TDC:15.02.26) (M/s KRIL Tirupati JV) | 15.02.26 | Coal Load(ESP-Under Approval) | 30.10.25 | 20.11.25 | 05.11.25 | 25.11.25 | 10.11.25 | _ | 15.01.26 | ESP not Approved TDC-10.10.25 Building Work is under progress. TDC-15.01.26 | Dy.CSTE(project)-R
28 | Coal Empty Yard Replacement PI to EI (TDC:15.03.26) (M/s KRIL Tirupati JV) | 15.03.26 | Coal Empty(ESP-Under Approval) | 30.10.25 | 15.11.25 | 05.11.25 | 30.11.25 | 15.11.25 | _ | 15.02.26 | EESSPP nnoott AApppprroovveedd TDC-12.10.25 Building Work is under progress. TDC-31.01.26 | Dy.CSTE(project)-R
29 | Dongargarh(DGG) UP Addl loop line. (TDC:15.11.25) (Ms Tirupati Enterprises Bilaspur) | 15.11.25 | D o n g argarh(ESP- Approved) | Y | Y | Y | Y | Y | - | Y | CRS sanction received on 04.10.25 | Dy. CSTE(Project)-NGP
30 | Samnapur Additional Loopline Work 30.01.25 (Ms Tungsten Rail & Infra Nagpur) | 30.01.2026 | S a m napur(ESP- Approved) | Y | Y | Y | Y | Y | - | Y | CRS application submitted on 16.10.25 | Dy. CSTE(Project)-NGP
31 | Gwarighat Addl loop line. TDC: 15.02.26 (Ms Tungsten Rail & Infra Nagpur) | 15.02.2026 | Gwarighat(ESP- Approved) | Y | Y | Y | Y | 28.10.25 | - | 30.10.25 | SIP under revision | Dy. CSTE(Project)-NGP
32 | Auto signaling work in Kalumna Jn Cabin- Godhni Chord cabin section. TDC: 20.03.2026 (Ms Tirupati Enterprises Bilaspur) | 20.03.2026 | Kalumna Jn Cabin, Godhni Chord Cabin | Cabin)-Y, N(Godhni Chord Cabin)- N | 30.10.25 | 25.10.2 5 | 15.11.25 | 22.11.25 | - | 31.01.26 | SAG inspection: 15.03.26 ( Signal: 02/14) Training certificate: 22.03.26 | Dy. CSTE(Project)-NGP
33 | Chandafort (CAF) Chord line Phase- I TDC: 31.12.2025 M/s Nandi Enterprizes. | 31.12.2025 | Chandafort(ESP- Approved) | 30.10.25 | 07.11.25 | 07.11.25 | 22.11.25 | 22.11.25 | - | 30.11.25 | S&T Tender awarded on 06.10.25. Engineering Tender is under Finalization | Dy. CSTE(Project)-NGP
34 | Conversation of Goods Siding at Keolari(KLZ) from Half length to full length. TDC: 28.02.2026 M/s Nandi Enterprozes. | 28.02.2026 | Keolari((ESP-Approved) | Y | 07.11.25 | 07.11.25 | 22.11.25 | 22.11.25 | - | 30.12.25 | S&T Tender awarded on 06.10.25. Engineering Tender is under Finalization | Dy. CSTE(Project)-NGP